## Sheet1
Event Marketing Plan Timeline | Up to 2 Months | 1 Month | 1 Week | EVENT | 1 Week
Planning
Assemble team
Define event objectives & measurements
Define activity mix (press announcement, happy hours, dinners, raffles, etc.)
Develop content plan including giveaway, if relevant
Determine exhibit, session needs
Make necessary reservations
Meeting Making
Obtain registration, press and speaker list
Develop target account/contact list from registration list
Extend meeting invites; promote booth # (multi-channel: SDRs, AEs, Marketing emails, digital ads, direct mail)
Team Prep
Briefing document (show info/hours, mandatory booth hours, booth schedule, lead goals, messaging, VIPs/speakers, all attendees cell phone #s)
Presentation materials - sessions, booth
Pre-set meeting schedule
Customer & prospect messaging/FAQ
Parallel event registration list (if relevant)
Go Time
Socialize session excerpts, photos & videos from booth, etc.
Capture customer testimonials/video for reuse
Produce daily blog or podcast from show floor
Meetings held
Post Event Follow Up
Team AAR (After Action Review) & KPI read-out
Send summary email to Biz Dev/Sales team (results, CRM data, actions, post-event nurture plan)
Segment/enter leads in CRM
Obtain final attendee list from event producers
Draft 'thanks for attending session/visiting booth' emails
Send 'thanks for attending session/visiting booth' emails
Draft 'sorry we missed you' emails
Send 'sorry we missed you' emails
Develop plan for leveraging/repurposing show content